## Overview
NORAM Account Executive Onboarding
From Day 1 to first Propose: a 90-day path built for selling payments at Checkout.com
Jasmine Jancsik, Lead Enablement, US · v1 draft, October 2026
Sessions mapped
Ready today
Need refresh
To build
Build/refresh items done
Phase | Days | Theme | Goal | Target selling time
Pre-board | Before Day 1 | Arrive ready | Day 1 is about people, not passwords. Tools, plan and buddy are in place before the AE walks in. | 0%
Land | Days 1–14 | Belong & orient | Understand how Checkout sells, who's who, the territory and the rules of engagement. Payments is told as a story first, then studied as a curriculum. | ≤10%
Learn | Days 15–30 | Payments & product fluency | Explain all five pillars in a merchant's language, see each pillar in live deals, and start call reviews and account planning. | 20%
Practice | Days 31–60 | Verticals, process & discovery | Go deep on NORAM verticals and the deal machine (deal desk, underwriting, partners), then prove discovery skills in the Day 60 Explore stack. | 50%
Perform | Days 61–90 | Price, propose & close | Price a deal, build a business case and present a tailored Checkout pitch. Graduation is the Day 90 Pitch Deck Certification. | 70%
Everboard | Day 90+ | Keep growing | Recurring skills sessions, call clinics and yearly recertification keep tenured AEs sharp. | 90%+
Milestone | Day | What | Pass mark
Day 30 Checkpoint | 30 | Elevator pitch sign-off + five-pillar knowledge check | Pitch approved by manager · ≥ 80% on the pillar knowledge check
Explore Call Certification | 60 | Live simulated Explore call with a payments persona, scored on a 7-part rubric | ≥ 80% overall and no section below 3/5
Pitch Deck Certification | 90 | Tailored pitch deck for a real territory account, presented to a panel | ≥ 80% overall and no section below 3/5

## Inventory
Every AE onboarding session: what exists today (Ready), what needs updating (Refresh) and what's missing (Build).
Phase | Week | Session | Category | Format | Hours | Owner | Status | Stack | What needs to happen / notes | Source
Pre-board (Before Day 1) | 0 | Welcome pack, 90-day plan & personal tracker issued | Foundations | Self-paced | 0.5 | Enablement | Build |  | Send the personal tracker (Karlie Chen format) and this 90-day map before Day 1 so the new hire arrives knowing the path. | Karlie Tracker
Pre-board (Before Day 1) | 0 | Tool access pre-provisioned (Salesforce, Clari, Apollo, LinkedIn Sales Nav, Highspot, Glean) | Tools & Process | Self-paced | 0 | Enablement + IT | Refresh |  | Today this takes a Day 1 session. Request access at offer-accept so Day 1 can go to people and context. | Q4 Plan
Pre-board (Before Day 1) | 0 | Buddy assigned + manager welcome call | People & Network | Live | 0.5 | Line manager | Refresh |  | Buddies are used informally (elevator pitch, role plays). Formalise it with a one-page buddy guide and a weekly 30-minute slot. | Karlie Tracker
Land (Days 1–14) | 1 | IT, People & Benefits inductions | Foundations | Live | 3 | People Team | Ready |  |  | Q4 Plan
Land (Days 1–14) | 1 | Your onboarding plan: the 30/60/90 kickoff | Foundations | Live | 0.5 | Enablement | Ready |  |  | Q4 Plan
Land (Days 1–14) | 1 | Intro to Checkout's Revenue Org (Global + NORAM) | Foundations | Live | 1.5 | Michel Tornabene | Ready |  |  | Karlie Tracker
Land (Days 1–14) | 1 | Mandatory compliance training (Nova) | Foundations | Self-paced | 3 | New hire | Ready |  |  | Q4 Plan
Land (Days 1–14) | 1 | Payments at Checkout in 60 minutes | Payments & Product | Live | 1 | Enablement + Solutions Engineering | Build |  | A story-led primer: the life of a card transaction, where Checkout earns, and why merchants switch. It replaces the Day 2 deep dive into Payments Academy and gives context before the curriculum starts. | New
Land (Days 1–14) | 1 | Sales Tools & Chrome Extensions | Tools & Process | Live | 1 | J.J. Henry | Ready |  |  | Karlie Tracker
Land (Days 1–14) | 1 | Finding answers: Highspot, Confluence & Glean | Tools & Process | Live | 1 | Enablement | Refresh |  | Update for the Highspot→Drive transition and Glean adoption (charter priority 3). | Q4 Plan
Land (Days 1–14) | 1 | Office hours with the NORAM GM | People & Network | Live | 0.5 | Zack Levine | Ready |  |  | Q4 Plan
Land (Days 1–14) | 1 | RevWay 0–1: Intro to Revenue Way & Buyer Psychology | Sales Skills | Self-paced | 2.5 | Self-directed | Ready |  |  | Q4 Plan
Land (Days 1–14) | 1 | Meet your pod + buddy coffee | People & Network | Practice | 1 | Pod leader | Ready |  |  | Q4 Plan
Land (Days 1–14) | 2 | Buyer personas in payments (Head of Payments, CFO, CPO, Eng) | Sales Skills | Live | 1 | J.J. Henry | Ready |  |  | Karlie Tracker
Land (Days 1–14) | 2 | Competitive Landscape | Payments & Product | Live | 1 | Michel Tornabene | Ready |  |  | Q4 Plan
Land (Days 1–14) | 2 | Territory planning (STP), Rules of Engagement & Incentive Ratings | Tools & Process | Live | 1 | Francesco Falcone | Ready |  | Must be live and finished by the end of Week 2. Francesco asked for this ASAP, early Week 3 at the latest. | Q4 Plan
Land (Days 1–14) | 2 | Salesforce, Clari & pipeline hygiene | Tools & Process | Live | 1 | Francesco Falcone | Ready |  |  | Q4 Plan
Land (Days 1–14) | 2 | AI in Commercial | Tools & Process | Live | 1 | Molly McKenna | Ready |  |  | Q4 Plan
Land (Days 1–14) | 2 | Meet the team: Sales, AM, Financial Partnerships, Partnerships, SE, RevOps | People & Network | Live | 3 | Team leads | Ready |  | Six 30-minute intros, using the prioritised Who-to-Meet list from the NY repository. | NY Repository
Land (Days 1–14) | 2 | Payments Academy: Foundations modules 1–5 | Payments & Product | Self-paced | 2.5 | Self-directed | Refresh |  | Moved from Day 2 to Week 2 and paced at about 30 minutes a day, after the 60-minute primer, with a Friday live debrief. | Q4 Plan
Land (Days 1–14) | 2 | RevWay 2–3: DEPTH Selling & Managing Pipeline | Sales Skills | Self-paced | 2.5 | Self-directed | Ready |  |  | Q4 Plan
Land (Days 1–14) | 2 | Friday knowledge check (Kahoot, pod leads join), runs weekly | Payments & Product | Practice | 0.5 | Enablement + pod leads | Ready |  |  | Q4 Plan
Learn (Days 15–30) | 3 | Payments Academy: Foundations 6–10 + live debrief | Payments & Product | Self-paced | 3 | Enablement | Refresh |  | Finish the Foundations here, not in Week 1. The debrief turns the modules into talk-tracks. | Q4 Plan
Learn (Days 15–30) | 3 | Product Foundations: Connect & Move | Payments & Product | Self-paced | 2 | Self-directed | Ready |  |  | Karlie Tracker
Learn (Days 15–30) | 3 | Pillars in live deals: Connect & Move (30 min each) | Payments & Product | Live | 1 | Pod leads | Refresh |  | Replace the generic 'sales perspective' sessions with 30-minute walk-throughs of live deals, built on a vertical use case (Francesco's feedback). | Q4 Plan
Learn (Days 15–30) | 3 | International Outlook: acquiring set-ups & cross-border | Payments & Product | Live | 0.75 | Michel Tornabene | Ready |  |  | Q4 Plan
Learn (Days 15–30) | 3 | Commercial Risk | Payments & Product | Live | 0.5 | Michel Tornabene | Ready |  |  | Karlie Tracker
Learn (Days 15–30) | 3 | Intro to NORAM verticals & where we win | Payments & Product | Live | 0.75 | Francesco Falcone | Ready |  | Pair this with the North America Vertical List in the NY repository. | Q4 Plan
Learn (Days 15–30) | 3 | Weekly call-review hour begins (Clari gametapes) | Sales Skills | Practice | 1 | Jim Cho + Francesco Falcone | Ready |  | Starts in Week 3, not Week 1, then runs weekly (Francesco's feedback). | Q4 Plan
Learn (Days 15–30) | 3 | Outreach lab: openers, email personalisation & gatekeepers | Sales Skills | Live | 2 | J.J. Henry | Ready |  |  | Karlie Tracker
Learn (Days 15–30) | 4 | Product Foundations: Protect, Boost & Manage | Payments & Product | Self-paced | 2.5 | Self-directed | Ready |  |  | Karlie Tracker
Learn (Days 15–30) | 4 | Pillars in live deals: Protect, Boost & Manage | Payments & Product | Live | 1 | Pod leads | Refresh |  | Same 30-minute live-deal format as Week 3. | Q4 Plan
Learn (Days 15–30) | 4 | Payment Performance AMA (Boost) | Payments & Product | Live | 1 | Daniel Linder | Ready |  | Focus on Boost, Daniel's pillar. | Q4 Plan
Learn (Days 15–30) | 4 | Account list review: your Top 70 | Sales Skills | Practice | 1 | Line manager | Ready |  |  | Karlie Tracker
Learn (Days 15–30) | 4 | RevWay 4–5: Discovery & Explore phases | Sales Skills | Self-paced | 2.5 | Self-directed | Ready |  |  | Q4 Plan
Learn (Days 15–30) | 4 | Cold-call role play | Sales Skills | Practice | 0.5 | J.J. Henry | Ready |  |  | Karlie Tracker
Learn (Days 15–30) | 4 | Day 30 Checkpoint: elevator pitch + five-pillar knowledge check | Certification | Certification | 1 | Line manager + Enablement | Refresh | Day 30 | Combine today's elevator-pitch reviews and pillar Kahoots into one recorded gate. | Karlie Tracker
Practice (Days 31–60) | 5 | Vertical deep dives: Digital Content and Ecommerce | Payments & Product | Live | 1.5 | Jules Gay / Katie Wile | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 5 | Vertical deep dives: Neobank & Remittance (AFT/OCT), Consumer Lending & Proptech | Payments & Product | Live | 1.5 | Olivia Smith / Octavio Balcazar | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 5 | Intro to Deal Management & Deal Desk | Tools & Process | Live | 0.5 | Faith Bergman | Ready |  |  | Karlie Tracker
Practice (Days 31–60) | 5 | Partner ecosystem: who we sell with and how | Payments & Product | Live | 1 | Jim Cho / Francesco Falcone / Jaime Yeager | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 5 | Build your prospecting cadence (Apollo) | Sales Skills | Practice | 0.5 | Ronak Bali | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 6 | ISV, Marketplace & MoR deep dive | Payments & Product | Live | 0.5 | Michael Taylor | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 6 | Pay to Card, Pay to Bank & FX | Payments & Product | Live | 1 | Olivia Smith | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 6 | Visa Direct: AFTs & card payouts | Payments & Product | Live | 0.5 | Amber McClure | Refresh |  | Paused while partnership terms are revamped. Bring it back when the new terms are ready. | Q4 Plan
Practice (Days 31–60) | 6 | Technical integration & merchant onboarding experience | Tools & Process | Live | 0.5 | Michael Taylor + Faith Bergman | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 6 | Underwriting overview | Tools & Process | Live | 1 | Jack Pontarelli | Ready |  |  | Karlie Tracker
Practice (Days 31–60) | 6 | RevWay 6–7: Questioning, funnel technique & listening | Sales Skills | Self-paced | 3 | Self-directed | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 7 | Voice of the customer: Head of Payments panel | Payments & Product | Live | 1.5 | Jaime Yeager / Jim Cho | Build |  | Planned in both SME trackers but never scheduled. Heads of Payments share what resonated in outreach and what didn't. | Q4 Plan
Practice (Days 31–60) | 7 | Top-rep Q&A, every two weeks | People & Network | Live | 0.5 | Sam Boukhiam / Louis Taupin | Build |  | Planned to 'start in Month 2' but never started. Sam's notes in the Q4 plan are the starting agenda. | Q4 Plan
Practice (Days 31–60) | 7 | Vertical deep dives: Insurance and Gaming & Gambling | Payments & Product | Live | 1 | Olivia Smith / Aaron Popack | Refresh |  | Both on hold ('wait for now'). Run Insurance virtually first. | Q4 Plan
Practice (Days 31–60) | 7 | Canada & the Canadian market | Payments & Product | Live | 0.5 | Yousef Almawy | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 7 | Role play with your pod lead | Sales Skills | Practice | 0.5 | Pod leads | Ready |  |  | Q4 Plan
Practice (Days 31–60) | 8 | Competitive deal clinic + refreshed battlecards | Sales Skills | Live | 1 | Jim Cho | Refresh |  | The 'Why Checkout Wins' battlecard is flagged as outdated. Release refreshed battlecards with this session. | NY Repository
Practice (Days 31–60) | 8 | Payment performance metrics that matter (auth rates, declines, tokens, cost) | Payments & Product | Live | 1 | Solutions Engineering + Product | Build |  | The numbers an AE has to quantify in discovery. Builds on the Decline Code and PPA cheat sheets. | New
Practice (Days 31–60) | 8 | Explore call gametapes: what great sounds like | Sales Skills | Practice | 1 | Jim Cho + Francesco Falcone | Refresh |  | Curate an Explore-only playlist in the Clari USA call repo, with timestamps to listen for. | NY Repository
Practice (Days 31–60) | 9 | Explore Call Masterclass: running discovery the Checkout way | Sales Skills | Live | 1.5 | Enablement + top AE | Build | Day 60 stack | Live, AE-specific application of RevWay 5–6: agenda, upfront contract, DEPTH funnel and summarise-to-commit. | New
Practice (Days 31–60) | 9 | Payments discovery question bank & value hypothesis | Sales Skills | Live | 1 | Enablement + Solutions Engineering | Build | Day 60 stack | Questions by persona and pillar, plus a one-page value-hypothesis template (auth uplift, fraud, cost, APM coverage, payouts). | New
Practice (Days 31–60) | 9 | Explore role-play sprint | Sales Skills | Practice | 1.5 | Pod leads + buddy | Ready | Day 60 stack | Three timed reps against three personas, with feedback on the certification rubric. | Q4 Plan
Practice (Days 31–60) | 9 | ★ Explore Call Certification | Certification | Certification | 1 | Pod lead + Enablement | Build | Day 60 stack | See the certification rubric. | New
Practice (Days 31–60) | 9 | Day 60 review: pipeline, activity & ramp check | Tools & Process | Practice | 0.5 | Line manager | Build | Day 60 stack | A structured 1:1 on pipeline created, meetings booked and cert results, with the next 30-day plan. | New
Perform (Days 61–90) | 10 | Propose Masterclass | Sales Skills | Live | 1.5 | Enablement | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 10 | Pricing guidance & take rate | Tools & Process | Live | 1 | Jim Cho + Francesco Falcone | Build |  | Listed in the Q3 SME tracker but never scheduled. Covers guardrails, approvals and how to talk about price. | Q4 Plan
Perform (Days 61–90) | 10 | Pricing calculator walk-through (real deal example) | Tools & Process | Live | 1 | Jim Cho | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 10 | AFT/OCT pricing calculator walk-through | Tools & Process | Live | 0.5 | Vladimir Sterenko | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 10 | RevWay 8–9: Propose & Presentation Skills | Sales Skills | Self-paced | 3.5 | Self-directed | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 11 | Payments economics: interchange++, fee & cost analysis | Payments & Product | Live | 1.5 | Deal Management + Solutions Engineering | Build |  | The resources exist (Gopuff and Rhino + Jetty cost analyses, L2/L3 interchange) and are tagged 'cover later', but there's no session. | NY Repository
Perform (Days 61–90) | 11 | Trade, deal structure & negotiation case studies | Sales Skills | Live | 1 | Pod lead (TBD) | Build |  | Negotiation, getting pricing approved, and minimum billing. The owner is still TBD in the SME tracker. | Q4 Plan
Perform (Days 61–90) | 11 | Underwriting from the UW lens + MAF & questionnaires | Tools & Process | Live | 1 | Jarett Israel + Rithvik Nair | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 11 | Objection handling drill + RevWay 10 | Sales Skills | Practice | 1.5 | Enablement | Refresh |  | Self-paced only today. Add a live drill that uses the competitive defense playbook. | Q4 Plan
Perform (Days 61–90) | 12 | How to ramp a merchant: what happens after 'yes' | Tools & Process | Live | 0.5 | Nicholas Schaffer | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 12 | QBR walk-through | Tools & Process | Live | 0.5 | Perrin Heyka | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 12 | MBO, quota mechanics & your path to quota | Tools & Process | Live | 1 | Francesco Falcone + Jim Cho | Refresh |  | Reschedule to 60 minutes with Jim, and invite newer hires. | Q4 Plan
Perform (Days 61–90) | 12 | Working with Marketing & the Strategic Accounts Team | People & Network | Live | 1 | Marketing + Cyril Chemla | Ready |  |  | Q4 Plan
Perform (Days 61–90) | 13 | Storyline workshop: building a Checkout pitch deck | Sales Skills | Live | 1.5 | Enablement + Product Marketing | Build | Day 90 stack | Insight → value → proof → plan, using the Great Decks library (GM, 1800 Contacts, Flutter RFP, Caesars). | NY Repository
Perform (Days 61–90) | 13 | Business case lab: quantify the value | Sales Skills | Practice | 1 | Solutions Engineering + Deal Management | Build | Day 90 stack | Turn the Day 60 value hypothesis into numbers using the pricing model and cost-analysis examples. | New
Perform (Days 61–90) | 13 | Deck peer review & dry run | Sales Skills | Practice | 1 | Buddy + pod | Build | Day 90 stack |  | New
Perform (Days 61–90) | 13 | ★ Pitch Deck Certification | Certification | Certification | 1 | Panel: pod lead, SE, Enablement, guest leader | Build | Day 90 stack | See the certification rubric. | New
Perform (Days 61–90) | 13 | Day 90 review & graduation to everboarding | Tools & Process | Practice | 0.5 | Line manager + Enablement | Build | Day 90 stack | Ramp review against quota trajectory, certifications logged, and an individual development plan for Days 91–180. | New
Everboard (Day 90+) | 14 | Monthly sales skills session | Sales Skills | Live | 1 | Enablement | Ready |  |  | Q4 Plan
Everboard (Day 90+) | 14 | 'How We Did It' at the sales all-hands | Sales Skills | Live | 0.5 | Octavio Balcazar / Olivia Smith | Ready |  |  | Q4 Plan
Everboard (Day 90+) | 14 | Call recording clinic, every two months | Sales Skills | Practice | 0.75 | Jim Cho + Francesco Falcone | Ready |  |  | Q4 Plan
Everboard (Day 90+) | 14 | Yearly recertification: Explore & Pitch | Certification | Certification | 1 | Enablement | Build |  | Keeps the bar consistent for tenured AEs (charter pillar 1: recertification rate). | New

## Build Backlog
P1 = needed for the next cohort (certifications, Day 60/90 stacks, Day 1 payments primer). Update Progress as content is built.
Priority | Type | Session | Phase | Week | Proposed owner | Target date | Progress | Content link | Brief
P1 | Build | Payments at Checkout in 60 minutes | Land (Days 1–14) | 1 | Enablement + Solutions Engineering |  | Not started |  | A story-led primer: the life of a card transaction, where Checkout earns, and why merchants switch. It replaces the Day 2 deep dive into Payments Academy and gives context before the curriculum starts.
P1 | Build | Explore Call Masterclass: running discovery the Checkout way | Practice (Days 31–60) | 9 | Enablement + top AE |  | Not started |  | Live, AE-specific application of RevWay 5–6: agenda, upfront contract, DEPTH funnel and summarise-to-commit.
P1 | Build | Payments discovery question bank & value hypothesis | Practice (Days 31–60) | 9 | Enablement + Solutions Engineering |  | Not started |  | Questions by persona and pillar, plus a one-page value-hypothesis template (auth uplift, fraud, cost, APM coverage, payouts).
P1 | Build | ★ Explore Call Certification | Practice (Days 31–60) | 9 | Pod lead + Enablement |  | Not started |  | See the certification rubric.
P1 | Build | Day 60 review: pipeline, activity & ramp check | Practice (Days 31–60) | 9 | Line manager |  | Not started |  | A structured 1:1 on pipeline created, meetings booked and cert results, with the next 30-day plan.
P1 | Build | Storyline workshop: building a Checkout pitch deck | Perform (Days 61–90) | 13 | Enablement + Product Marketing |  | Not started |  | Insight → value → proof → plan, using the Great Decks library (GM, 1800 Contacts, Flutter RFP, Caesars).
P1 | Build | Business case lab: quantify the value | Perform (Days 61–90) | 13 | Solutions Engineering + Deal Management |  | Not started |  | Turn the Day 60 value hypothesis into numbers using the pricing model and cost-analysis examples.
P1 | Build | Deck peer review & dry run | Perform (Days 61–90) | 13 | Buddy + pod |  | Not started
P1 | Build | ★ Pitch Deck Certification | Perform (Days 61–90) | 13 | Panel: pod lead, SE, Enablement, guest leader |  | Not started |  | See the certification rubric.
P1 | Build | Day 90 review & graduation to everboarding | Perform (Days 61–90) | 13 | Line manager + Enablement |  | Not started |  | Ramp review against quota trajectory, certifications logged, and an individual development plan for Days 91–180.
P1 | Build | Yearly recertification: Explore & Pitch | Everboard (Day 90+) | 14 | Enablement |  | Not started |  | Keeps the bar consistent for tenured AEs (charter pillar 1: recertification rate).
P1 | Refresh | Day 30 Checkpoint: elevator pitch + five-pillar knowledge check | Learn (Days 15–30) | 4 | Line manager + Enablement |  | Not started |  | Combine today's elevator-pitch reviews and pillar Kahoots into one recorded gate.
P2 | Build | Welcome pack, 90-day plan & personal tracker issued | Pre-board (Before Day 1) | 0 | Enablement |  | Not started |  | Send the personal tracker (Karlie Chen format) and this 90-day map before Day 1 so the new hire arrives knowing the path.
P2 | Build | Voice of the customer: Head of Payments panel | Practice (Days 31–60) | 7 | Jaime Yeager / Jim Cho |  | Not started |  | Planned in both SME trackers but never scheduled. Heads of Payments share what resonated in outreach and what didn't.
P2 | Build | Top-rep Q&A, every two weeks | Practice (Days 31–60) | 7 | Sam Boukhiam / Louis Taupin |  | Not started |  | Planned to 'start in Month 2' but never started. Sam's notes in the Q4 plan are the starting agenda.
P2 | Build | Payment performance metrics that matter (auth rates, declines, tokens, cost) | Practice (Days 31–60) | 8 | Solutions Engineering + Product |  | Not started |  | The numbers an AE has to quantify in discovery. Builds on the Decline Code and PPA cheat sheets.
P2 | Build | Pricing guidance & take rate | Perform (Days 61–90) | 10 | Jim Cho + Francesco Falcone |  | Not started |  | Listed in the Q3 SME tracker but never scheduled. Covers guardrails, approvals and how to talk about price.
P2 | Build | Payments economics: interchange++, fee & cost analysis | Perform (Days 61–90) | 11 | Deal Management + Solutions Engineering |  | Not started |  | The resources exist (Gopuff and Rhino + Jetty cost analyses, L2/L3 interchange) and are tagged 'cover later', but there's no session.
P2 | Build | Trade, deal structure & negotiation case studies | Perform (Days 61–90) | 11 | Pod lead (TBD) |  | Not started |  | Negotiation, getting pricing approved, and minimum billing. The owner is still TBD in the SME tracker.
P2 | Refresh | Tool access pre-provisioned (Salesforce, Clari, Apollo, LinkedIn Sales Nav, Highspot, Glean) | Pre-board (Before Day 1) | 0 | Enablement + IT |  | Not started |  | Today this takes a Day 1 session. Request access at offer-accept so Day 1 can go to people and context.
P2 | Refresh | Buddy assigned + manager welcome call | Pre-board (Before Day 1) | 0 | Line manager |  | Not started |  | Buddies are used informally (elevator pitch, role plays). Formalise it with a one-page buddy guide and a weekly 30-minute slot.
P2 | Refresh | Finding answers: Highspot, Confluence & Glean | Land (Days 1–14) | 1 | Enablement |  | Not started |  | Update for the Highspot→Drive transition and Glean adoption (charter priority 3).
P2 | Refresh | Payments Academy: Foundations modules 1–5 | Land (Days 1–14) | 2 | Self-directed |  | Not started |  | Moved from Day 2 to Week 2 and paced at about 30 minutes a day, after the 60-minute primer, with a Friday live debrief.
P2 | Refresh | Payments Academy: Foundations 6–10 + live debrief | Learn (Days 15–30) | 3 | Enablement |  | Not started |  | Finish the Foundations here, not in Week 1. The debrief turns the modules into talk-tracks.
P2 | Refresh | Pillars in live deals: Connect & Move (30 min each) | Learn (Days 15–30) | 3 | Pod leads |  | Not started |  | Replace the generic 'sales perspective' sessions with 30-minute walk-throughs of live deals, built on a vertical use case (Francesco's feedback).
P2 | Refresh | Pillars in live deals: Protect, Boost & Manage | Learn (Days 15–30) | 4 | Pod leads |  | Not started |  | Same 30-minute live-deal format as Week 3.
P2 | Refresh | Visa Direct: AFTs & card payouts | Practice (Days 31–60) | 6 | Amber McClure |  | Not started |  | Paused while partnership terms are revamped. Bring it back when the new terms are ready.
P2 | Refresh | Vertical deep dives: Insurance and Gaming & Gambling | Practice (Days 31–60) | 7 | Olivia Smith / Aaron Popack |  | Not started |  | Both on hold ('wait for now'). Run Insurance virtually first.
P2 | Refresh | Competitive deal clinic + refreshed battlecards | Practice (Days 31–60) | 8 | Jim Cho |  | Not started |  | The 'Why Checkout Wins' battlecard is flagged as outdated. Release refreshed battlecards with this session.
P2 | Refresh | Explore call gametapes: what great sounds like | Practice (Days 31–60) | 8 | Jim Cho + Francesco Falcone |  | Not started |  | Curate an Explore-only playlist in the Clari USA call repo, with timestamps to listen for.
P2 | Refresh | Objection handling drill + RevWay 10 | Perform (Days 61–90) | 11 | Enablement |  | Not started |  | Self-paced only today. Add a live drill that uses the competitive defense playbook.
P2 | Refresh | MBO, quota mechanics & your path to quota | Perform (Days 61–90) | 12 | Francesco Falcone + Jim Cho |  | Not started |  | Reschedule to 60 minutes with Jim, and invite newer hires.

## Explore Call Cert
Explore Call Certification
When | Day 60 (Week 9)
Format | A 30-minute live, simulated Explore call. The assessor plays a scripted payments persona (e.g. Head of Payments at a mid-market subscription merchant). Recorded in Clari.
Assessors | Pod lead + Enablement (calibrated on the same rubric)
Pass mark | ≥ 80% overall (28/35) and no section below 3/5. One retake within 10 working days, with coaching.
AE name
Assessor
Date
Section | What good looks like | Score (1–5) | Evidence / coaching notes
Pre-call research & hypothesis | Knows the merchant's model, footprint, likely PSP set-up and a starting hypothesis
Opening & upfront contract | Clear agenda, time check and agreed outcome for the call
DEPTH questioning funnel | Moves from broad to specific, with open questions and no early pitching
Payments pain quantified | Uncovers and sizes at least one pain: auth rate, fraud, cost, APMs or payouts
Pillar mapping | Links the pains to the right Checkout pillar and capability
Listening & summarising | Listens far more than talks, and plays the summary back accurately
Committed next step | A dated next step with the right stakeholders
Total |  |  | out of 35
Result

## Pitch Deck Cert
Pitch Deck Certification
When | Day 90 (Week 13)
Format | A tailored deck for a real territory account: a 20-minute presentation plus 10 minutes of panel Q&A, with the panel playing the buying committee.
Assessors | Pod lead, Solutions Engineer, Enablement, plus a guest leader
Pass mark | ≥ 80% overall (32/40) and no section below 3/5. Exemplary decks go into the Great Decks library.
AE name
Assessor
Date
Section | What good looks like | Score (1–5) | Evidence / coaching notes
Merchant insight | Opens with the merchant's world and priorities, not ours
Value narrative | Story connects their goals to Checkout pillars with clear outcomes
Business case | Quantified value (auth uplift, cost, fraud, ops) using their data
Proof | Relevant case studies, references or NPS evidence for the vertical
Competitive differentiation | Positions against the incumbent without disparaging them
Pricing narrative | Commercials framed within guidance, linked to value
Mutual action plan | Clear path to signature, integration and go-live
Executive presence & Q&A | Confident, concise, handles objections calmly
Total |  |  | out of 40
Result

## New Hire Tracker
AE Onboarding Tracker: make a copy for each new hire
Progress
Name: |  |  | Region:
Job title: |  |  | Line manager:
Start date: |  |  | Enablement manager:
Buddy: |  |  | Cohort:
Week | Target date | Session | Format | Owner | Complete? | My notes
Pre-board |  | Welcome pack, 90-day plan & personal tracker issued | Self-paced | Enablement | FALSE
Pre-board |  | Tool access pre-provisioned (Salesforce, Clari, Apollo, LinkedIn Sales Nav, Highspot, Glean) | Self-paced | Enablement + IT | FALSE
Pre-board |  | Buddy assigned + manager welcome call | Live | Line manager | FALSE
Week 1 |  | IT, People & Benefits inductions | Live | People Team | FALSE
Week 1 |  | Your onboarding plan: the 30/60/90 kickoff | Live | Enablement | FALSE
Week 1 |  | Intro to Checkout's Revenue Org (Global + NORAM) | Live | Michel Tornabene | FALSE
Week 1 |  | Mandatory compliance training (Nova) | Self-paced | New hire | FALSE
Week 1 |  | Payments at Checkout in 60 minutes | Live | Enablement + Solutions Engineering | FALSE
Week 1 |  | Sales Tools & Chrome Extensions | Live | J.J. Henry | FALSE
Week 1 |  | Finding answers: Highspot, Confluence & Glean | Live | Enablement | FALSE
Week 1 |  | Office hours with the NORAM GM | Live | Zack Levine | FALSE
Week 1 |  | RevWay 0–1: Intro to Revenue Way & Buyer Psychology | Self-paced | Self-directed | FALSE
Week 1 |  | Meet your pod + buddy coffee | Practice | Pod leader | FALSE
Week 2 |  | Buyer personas in payments (Head of Payments, CFO, CPO, Eng) | Live | J.J. Henry | FALSE
Week 2 |  | Competitive Landscape | Live | Michel Tornabene | FALSE
Week 2 |  | Territory planning (STP), Rules of Engagement & Incentive Ratings | Live | Francesco Falcone | FALSE
Week 2 |  | Salesforce, Clari & pipeline hygiene | Live | Francesco Falcone | FALSE
Week 2 |  | AI in Commercial | Live | Molly McKenna | FALSE
Week 2 |  | Meet the team: Sales, AM, Financial Partnerships, Partnerships, SE, RevOps | Live | Team leads | FALSE
Week 2 |  | Payments Academy: Foundations modules 1–5 | Self-paced | Self-directed | FALSE
Week 2 |  | RevWay 2–3: DEPTH Selling & Managing Pipeline | Self-paced | Self-directed | FALSE
Week 2 |  | Friday knowledge check (Kahoot, pod leads join), runs weekly | Practice | Enablement + pod leads | FALSE
Week 3 |  | Payments Academy: Foundations 6–10 + live debrief | Self-paced | Enablement | FALSE
Week 3 |  | Product Foundations: Connect & Move | Self-paced | Self-directed | FALSE
Week 3 |  | Pillars in live deals: Connect & Move (30 min each) | Live | Pod leads | FALSE
Week 3 |  | International Outlook: acquiring set-ups & cross-border | Live | Michel Tornabene | FALSE
Week 3 |  | Commercial Risk | Live | Michel Tornabene | FALSE
Week 3 |  | Intro to NORAM verticals & where we win | Live | Francesco Falcone | FALSE
Week 3 |  | Weekly call-review hour begins (Clari gametapes) | Practice | Jim Cho + Francesco Falcone | FALSE
Week 3 |  | Outreach lab: openers, email personalisation & gatekeepers | Live | J.J. Henry | FALSE
Week 4 |  | Product Foundations: Protect, Boost & Manage | Self-paced | Self-directed | FALSE
Week 4 |  | Pillars in live deals: Protect, Boost & Manage | Live | Pod leads | FALSE
Week 4 |  | Payment Performance AMA (Boost) | Live | Daniel Linder | FALSE
Week 4 |  | Account list review: your Top 70 | Practice | Line manager | FALSE
Week 4 |  | RevWay 4–5: Discovery & Explore phases | Self-paced | Self-directed | FALSE
Week 4 |  | Cold-call role play | Practice | J.J. Henry | FALSE
Week 4 |  | Day 30 Checkpoint: elevator pitch + five-pillar knowledge check | Certification | Line manager + Enablement | FALSE
Week 5 |  | Vertical deep dives: Digital Content and Ecommerce | Live | Jules Gay / Katie Wile | FALSE
Week 5 |  | Vertical deep dives: Neobank & Remittance (AFT/OCT), Consumer Lending & Proptech | Live | Olivia Smith / Octavio Balcazar | FALSE
Week 5 |  | Intro to Deal Management & Deal Desk | Live | Faith Bergman | FALSE
Week 5 |  | Partner ecosystem: who we sell with and how | Live | Jim Cho / Francesco Falcone / Jaime Yeager | FALSE
Week 5 |  | Build your prospecting cadence (Apollo) | Practice | Ronak Bali | FALSE
Week 6 |  | ISV, Marketplace & MoR deep dive | Live | Michael Taylor | FALSE
Week 6 |  | Pay to Card, Pay to Bank & FX | Live | Olivia Smith | FALSE
Week 6 |  | Visa Direct: AFTs & card payouts | Live | Amber McClure | FALSE
Week 6 |  | Technical integration & merchant onboarding experience | Live | Michael Taylor + Faith Bergman | FALSE
Week 6 |  | Underwriting overview | Live | Jack Pontarelli | FALSE
Week 6 |  | RevWay 6–7: Questioning, funnel technique & listening | Self-paced | Self-directed | FALSE
Week 7 |  | Voice of the customer: Head of Payments panel | Live | Jaime Yeager / Jim Cho | FALSE
Week 7 |  | Top-rep Q&A, every two weeks | Live | Sam Boukhiam / Louis Taupin | FALSE
Week 7 |  | Vertical deep dives: Insurance and Gaming & Gambling | Live | Olivia Smith / Aaron Popack | FALSE
Week 7 |  | Canada & the Canadian market | Live | Yousef Almawy | FALSE
Week 7 |  | Role play with your pod lead | Practice | Pod leads | FALSE
Week 8 |  | Competitive deal clinic + refreshed battlecards | Live | Jim Cho | FALSE
Week 8 |  | Payment performance metrics that matter (auth rates, declines, tokens, cost) | Live | Solutions Engineering + Product | FALSE
Week 8 |  | Explore call gametapes: what great sounds like | Practice | Jim Cho + Francesco Falcone | FALSE
Week 9 |  | Explore Call Masterclass: running discovery the Checkout way | Live | Enablement + top AE | FALSE
Week 9 |  | Payments discovery question bank & value hypothesis | Live | Enablement + Solutions Engineering | FALSE
Week 9 |  | Explore role-play sprint | Practice | Pod leads + buddy | FALSE
Week 9 |  | ★ Explore Call Certification | Certification | Pod lead + Enablement | FALSE
Week 9 |  | Day 60 review: pipeline, activity & ramp check | Practice | Line manager | FALSE
Week 10 |  | Propose Masterclass | Live | Enablement | FALSE
Week 10 |  | Pricing guidance & take rate | Live | Jim Cho + Francesco Falcone | FALSE
Week 10 |  | Pricing calculator walk-through (real deal example) | Live | Jim Cho | FALSE
Week 10 |  | AFT/OCT pricing calculator walk-through | Live | Vladimir Sterenko | FALSE
Week 10 |  | RevWay 8–9: Propose & Presentation Skills | Self-paced | Self-directed | FALSE
Week 11 |  | Payments economics: interchange++, fee & cost analysis | Live | Deal Management + Solutions Engineering | FALSE
Week 11 |  | Trade, deal structure & negotiation case studies | Live | Pod lead (TBD) | FALSE
Week 11 |  | Underwriting from the UW lens + MAF & questionnaires | Live | Jarett Israel + Rithvik Nair | FALSE
Week 11 |  | Objection handling drill + RevWay 10 | Practice | Enablement | FALSE
Week 12 |  | How to ramp a merchant: what happens after 'yes' | Live | Nicholas Schaffer | FALSE
Week 12 |  | QBR walk-through | Live | Perrin Heyka | FALSE
Week 12 |  | MBO, quota mechanics & your path to quota | Live | Francesco Falcone + Jim Cho | FALSE
Week 12 |  | Working with Marketing & the Strategic Accounts Team | Live | Marketing + Cyril Chemla | FALSE
Week 13 |  | Storyline workshop: building a Checkout pitch deck | Live | Enablement + Product Marketing | FALSE
Week 13 |  | Business case lab: quantify the value | Practice | Solutions Engineering + Deal Management | FALSE
Week 13 |  | Deck peer review & dry run | Practice | Buddy + pod | FALSE
Week 13 |  | ★ Pitch Deck Certification | Certification | Panel: pod lead, SE, Enablement, guest leader | FALSE
Week 13 |  | Day 90 review & graduation to everboarding | Practice | Line manager + Enablement | FALSE

## Who to Meet
Aim to finish within your first month. Adapted from the NY Sales Class repository and Karlie Chen's tracker; update names per cohort.
Priority | Name | Why | Met?
P0 | Line manager & buddy | Your manager and day-to-day guide | FALSE
P0 | Jim Cho | VP Sales | FALSE
P1 | Michel Tornabene | Revenue Enablement | FALSE
P1 | Zack Levine | NORAM GM | FALSE
P1 | Faith Bergman | Deal Management lead | FALSE
P1 | Rithvik Nair | Your Deal Management contact | FALSE
P1 | Sandra Suen | BDR lead + RevOps strategy | FALSE
P1 | Jarett Israel + team | Underwriting | FALSE
P1 | Jaime Yeager / Louis Taupin / Luke Brauer | Pod leaders (ATL / SF / NY) | FALSE
P1 | Matt Baum, Mike O'Connor & Ezra Cohen | Financial Partnerships | FALSE
P1 | Cyril Chemla | Strategic Accounts Team | FALSE
P2 | Michael Taylor | TAM & SE lead | FALSE
P2 | Jeff Schmidt | Sales Engineering lead | FALSE
P2 | Adam Manassero / Perrin Heyka | Account Management | FALSE
P2 | Ginny Huber / Phoebe Caine | Partnerships | FALSE
P2 | Marketing team | Local marketing | FALSE
P2 | Max Totilo | US Compliance | FALSE
P3 | Sam Boukhiam | Top rep: tips & tricks | FALSE